## Team
Initials | First | Last | Email | GitHub Username | ScrumMaster
bs | Bemin | Shaker | bshaker1@stevens.edu | Bemin-shaker | No
pm | Phong | Mai | pmai@stevens.edu | vuawind | No
th | Tony | Huang | thuang12@stevens.edu | tonyhuang219 | No
sh | Steven | Hoang | shoang@stevens.edu | Fazootle | Yes
cr | Chris | Rodriguez | crodrig9@stevens.edu | chris-1013 | No
fy | Federico | Yacoubian | fyacoubi@stevens.edu | feddachini | No
|  |  | GitHub Repository: | https://github.com/tonyhuang219/CS555
|  |  | Kanban URL: | https://github.com/users/tonyhuang219/projects/2/views/1

## Backlog
Sprint | Story ID | Story Name | Owner | Status
1 | US06 | children see a todo list | Tony | Done
1 | US11 | Set up database & authentication | Bemin | Done
1 | US10 | Set up database & authentication | Steven | Done
1 | US12 | Set up database & authentication | Fed | Done
1 | US13 | Set up database & authentication | Chris | Done
1 | US07 | Parents/Children Login | Mai | Done
2 | US09 | Add metrics | Steven | Done
2 | US08 | Set priorities to task | Tony | Done

## Burndown README
The goal of the burndown chart is to help the agile team and customer to understand how the developers are doing
to deliver the product. Burndown charts can be done daily, weekly, at the end of a sprint, or at whatever time interval makes sense.
We'll update our burndown chart for the GEDCOM project at the end of each sprint.
At the end of each sprint, you should update the number of remaining stories, the LOC written to implement the user stories
implemented in this sprint, and the minutes needed to write those lines of code.
Here's a sample burndown chart for a team of three:
Sprint | Date | Remaining Stories | Story Velocity | LOC | Min | Code Velocity
Start | 2016-06-06 | 24 |  | 0
Sprint 1 | 2016-06-19 | 18 | 6 | 250 | 120 | 125
Sprint 2 | 2016-07-03 | 12 | 6 | 480 | 135 | 102.2222
Sprint 3 | 2016-07-17 | 6 | 6 | 740 | 160 | 97.5
Sprint 4 | 2016-07-31 | 0 | 6 | 1100 | 145 | 148.9655
= # team members * 4 sprints *
2 stories per sprint
lines of code per hour is calcuated by Excel
Velocity of completing user stories (calculated)
Total
LOC
How long to implement the user stories in this sprint
When we expect to complete all user stories

## Burndown
Date | Remaining Stories | Story Velocity | LOC | Min | Code Velocity
2014-09-22 | 13 |  | 0 | 0 |  | Start
2022-10-16 | 12 | 1 | 6072 | 2900 | 125.6276 | Sprint 1
2022-10-31 | 10 | 2 | 8822 | 5150 | 32.0388 | Sprint 2 end
2022-11-04 | 9 | 1 | 12942 | 11222 | 22.0282 | Sprint 3 end
2022-12-01 | 0 | 9 | 17272 | 15452 | 16.8134 | Sprint 4 end
#DIV/0!

## Sprint1
Story ID | Story Name | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed
US06 | children see a todo list | Tony |  | 750 | 920 | 210 | 350 | in progress
T06.01 | children select a date from a calendar | Tony |  | 300 | 400 | 0 | 0 | in progress
T06.02 | Display the list of tasks to do | Tony | in progress | 400 | 400 | 168 | 300 | Done
T06.03 | Can mark a task as finished | Tony | in progress | 50 | 120 | 20 | 50 | Done
T06.04 | Create readme | Tony | in progress | 30 | 30 | 22 | 20 | Done
US11 | Set up database & authentication | Bemin |  | 200 | 80 | 522 | 40
T11.01 | Create Firebase project & share with rest of team | Bemin | Done | 0 | 20 | 0 | 10 | Done
T11.02 | Create signup page for parent | Bemin | In progess | 200 | 60 | 522 | 30 | Done
US10 | Achievement/Reward Page | Steven |  | 700 | 1200 | 400 | 90
T10.01 | Children can redeem points | Steven |  | 300 | 400 | 50 | 30 | in progress
T10.02 | parents can set what children can redeem | Steven |  | 200 | 400 | 50 | 50 | in progress
T10.03 | parents can set the cost of what children can redeem | Steven |  | 200 | 400 | 50 | 50 | in progress
US12 | Parental control/ Setting | Fed |  | 600 | 600 | 270 | 180 | in progress
US13 | Children and parents want a calender page where they can see task for any given day | Chris |  | 400 | 330 | 570 | 240
T013.01 | Make the Calender interactive | Chris |  | 150 | 90 | 450 | 240 | Done
T013.02 | Sync the child and parent calender | Chris |  | 200 | 180 | 50 | 30 | In Progress
T013.03 | Easily switch between calender and todo list | Chris |  | 50 | 60 | 70 | 20 | In Progress
US07 | Parents Login | Mai | in progress | 600 | 600 | 2400 | 1000 | in progress
| Make username field interactive | Mai | in progress | 200 | 200 | 800 | 300 | in progress
| Make password field interactive | Mai | in progress | 200 | 200 | 800 | 300 | in progress
| Make login button interactive | Mai | in progress | 200 | 200 | 800 | 400 | in progress
US07 | Children Login | Mai | in progress | 400 | 400 | 1700 | 1000 | in progress
| Make number code field interactive | Mai | in progress | 200 | 200 | 850 | 500 | in progress
| Make login button interactive | Mai | in progress | 200 | 200 | 850 | 500 | in progress
[6 empty] | LOC | Min
[6 empty] | 6072 | 2900
things you want to keep doing
Keep using discord
keep using the kanban in github
For each commit, add a more detailed description
Communicate if user stories overlap.
Things to avoid
make sure to update the excel sheet
Avoid wating last second to do a commit (commit weekly)

## Sprint2
Story ID | Story Name | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed
US06 | children see a todo list | Tony | in progress | 750 | 920 | 210 | 350 | in progress
T06.01 | children select a date from a calendar | Tony | in progress | 300 | 400 | 300 | 300 | in progress
US01 | Set date, description, reward note to task | Tony | Done | 400 | 300 | 100 | 240 | Done
T01.01 | Parents set the deadlineand it will be updated on child's todo list | Tony | Done | 200 | 100 | 70 | 180 | Done
T01.02 | Parents set the rewards | Tony | Done | 200 | 200 | 30 | 60 | Done
US11 | Set up database & authentication | Bemin | In progess | 200 | 80 | 300 | 180 | Done
T11.01 | Connect signup page to Firebase Auth | Bemin | In progess | 100 | 60 | 100 | 60 | Done
US13 | Children and parents want a calender page where they can see task for any given day | Chris |  | 400 | 330 | 570 | 240
T013.01 | Sync the child and parent calender | Chris |  | 200 | 180 | 50 | 30 | In Progress
T013.02 | Easily switch between calender and todo list | Chris |  | 50 | 60 | 70 | 20 | Completed
US12 | Parental control/ Setting | Fed |  | 600 | 600 | 270 | 180 | in progress
US12.01 | Backend User Settings | Fed |  | 300 | 300 |  | 180 | in progress
US07 | Parents Login | Mai | done | 600 | 600 | 900 | 1000 | done
T07.01 | Make username field interactive | Mai | done | 200 | 200 | 300 | 300 | done
T07.02 | Make password field interactive | Mai | done | 200 | 200 | 300 | 300 | done
T07.03 | Make login button interactive | Mai | done | 200 | 200 | 300 | 400 | done
US07 | Children Login | Mai | in progress | 400 | 400 | 1700 | 1000 | in progress
T07.04 | Make number code field interactive | Mai | in progress | 200 | 200 | 850 | 500 | in progress
T07.05 | Make login button interactive | Mai | in progress | 200 | 200 | 850 | 500 | in progress
US09 | Add metrics | Steven | in progress | 400 | 400 | 400 | 60 | In Progress
T09.01 | Show How many tasks are completed | Steven | in progress | 200 | 200 | 200 | 300 | In Progress
T09.02 | Show How many tasks are uncompleted | Steven | in progress | 200 | 200 | 200 | 300 | In Progress
| things you want to keep doing | [5 empty] | Mins
| Keep using discord |  |  |  |  | 2750 | 2250
keep using the kanban in github
For each commit, add a more detailed description
Communicate if user stories overlap and work on merging to main
Assign new members tasks
Things to avoid
make sure to update the excel sheet
Avoid wating last second to do a commit (commit weekly)

## Sprint3
Story ID | Story Name | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed
US06 | children see a todo list | Tony | in progress | 750 | 920 | 700 | 300 | completed
T06.01 | children select a date from a calendar | Tony | in progress | 300 | 400 | 700 | 300 | completed
US02 | children get rewarded for completing task | Tony | started | 400 | 300 | 100 | 240 | started
US11 | Authentication | Bemin | In progess | 200 | 80 | 300 | 180 | Done
T11.02 | Improve UI of signup page | Bemin | In progess | 200 | 120 | 200 | 40 | Done
US07 | Children Login | Mai | in progress | 400 | 400 | 1700 | 1000 | in progress
T07.04 | Make number code field interactive | Mai | in progress | 200 | 200 | 850 | 500 | in progress
T07.05 | Make login button interactive | Mai | in progress | 200 | 200 | 850 | 500 | in progress
US07 | Parents Login | Mai | done | 200 | 200 | 450 | 500 | done
T07.06 | Connect with Firebase | Mai | done | 200 | 200 | 450 | 500 | done
US13 | Children and parents want a calender page where they can see task for any given day | Chris |  | 400 | 330 | 570 | 240
T013.01 | Sync the child and parent calender | Chris | in progress | 200 | 180 | 50 | 30 | In Progress
T013.02 | Sync task list with firebase tasks | Chris | in progress | 70 | 180 |  |  | In Progress
US12 | Parental control/ Setting | Fed |  | 600 | 600 | 270 | 180 | in progress
US12.01 | Backend User Settings | Fed |  | 300 | 300 |  | 180 | in progress
US12.02 | Sync User Settings with Firebase | Fed |  | 300 | 300 |  | 45 | in progress
US14 | Security Feature | Peace | in progress | 200 | 200 | 80 | 200 | progress
US09 | Add metrics | Steven | in progress | 400 | 400 | 400 | 60 | In Progress
T09.01 | Show How many tasks are completed | Steven | in progress | 200 | 200 | 400 | 500 | In Progress
T09.02 | Show How many tasks are uncompleted | Steven | in progress | 200 | 200 | 400 | 500 | In Progress
[6 empty] | 4120 | 2400
Things to Avoid
Make sure you do a commit every week. There are 2 weeks per sprint, so do 2 commit per week
Finish your user story. Every sprint you should do a new user story,
If you are unable to do your work, like you are waiting for someone else. 1) work on another user story. 2) meet half way and finish the stuff you can finish.
Things to do
Create unit tests. No one did this last week

## Sprint4
Story ID | Story Name | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed
US11 | Authentication | Bemin | completed | 200 | 80 | 300 | 180 | completed
T11.02 | Create 4-digit code feature for kids to signup | Bemin | completed | 200 | 120 | 200 | 120 | completed
US12 | Parental Control | Tony | completed | 400 | 600 | 700 | 420 | completed
T12.01 | Have different screens for parents and children | Tony | completed | 400 | 600 | 200 | 120 | completed
T12.02 | Children do not have access to creating tasks | Tony | completed | 400 | 600 | 300 | 180 | completed
T12.03 | Parents confirm that a task is completed | Tony | completed | 400 | 600 | 200 | 120 | completed
T12.04 | Add Unit tests |  |  | 800 | 400 | 600 | 410 | completed
US14 | Security Feature ¦ Authentication | Bemin, Mai, Tony | completed | 300 | 120 | 100 | 110 | completed
US14.01 | Security Feature ¦ Parental Control | Tony | completed | 200 | 80 | 300 | 180 | completed
US14.02 | Security Feature ¦ 4 Digit Child Login | Peace | completed | 200 | 200 | 200 | 120 | completed
US07 | Children Login | Mai | completed | 400 | 400 | 1700 | 1000 | completed
T07.04 | Make number code field interactive | Mai | completed | 200 | 200 | 850 | 500 | completed
T07.05 | Make login button interactive | Mai | completed | 200 | 200 | 850 | 500 | completed
US13 | Children and parents want a calender page where they can see task for any given day | Chris |  | 400 | 330 | 570 | 240
T013.01 | Sync the child and parent calender | Chris | completed | 200 | 180 | 70 | 120 | completed
T013.02 | Sync task list with firebase tasks | Chris | completed | 70 | 180 | 70 | 120 | completed
US09 | Refactoring | Steven | completed | 800 | 1000 | 230 | 990 | completed
T09.01 | Remove duplicate code | Steven | completed | 400 | 500 | 100 | 500 | completed
T09.02 | Improve the naming of functions | Steven | completed | 400 | 500 | 130 | 490 | completed
US09 | Refactoring | Fed | completed | 400 | 150 | 230 | 990 | completed
T09.01 | Make code more modular | Fed | completed | 300 | 150 | 100 | 500 | completed
[6 empty] | 4330 | 4230
Things We Love
New knowledged learned
The praticality of the app
Putting in the time to organize everything in the beginning, despite it being a headache saved us so much time later on
Lessons Learned
Communcation is key
The importance of having pull requests, instead of committing to the main branch
A better understanding of react native
Experience working using industry methods

## Stories
Story ID | Story Name | Story Description
US01 | Parents assign tasks to children | As a parent, I want to assign tasks to kids to make them productive
US02 | children get rewarded for completing task | As a child, I want my tasks to be tracked so I can get rewarded at the end
US03 | Parents wants to teach responsibility | As a parent, I want to assign tasks to kids so they can become more responsible.
US04 | Controlling the reward system | As a parent, I want a reward system so I can entice kids to do chore
US05 | Secure the database | As a parent, I want to the server to be secure so kids cannot tamper with data
US06 | children see a todo list | As a child, I want to be able to see the list of tasks for the day so I do not get in trouble.
US07 | Login screen | As a child, I want to be able to login so I can see the task list and progress
US08 | Set priorities to task | As a parent, I want to set the priorities of the different tasks to indicate the importance and urgency
US09 | Add metrics | As a parent, I want to track how many tasks my kids have done in a day/week/month
US10 | Achievement Page | As a child, I want to get rewarded when I hit a mile stone for how many chores I have finished or how consistent I was.
US11 | Set up the database | As a system, I want the database to keep track of all need chore data.
US12 | Parental control | As a parent, I want parental control like locking the chores for a day or the rewards allowed for a task
US13 | Calendar page | As a children or parent, we want a calender page where we can see task for any given day
US14 | Refactoring